## Project
Project Engineer | Project year | Order number | Customer | Project | Product | Design | Manufactured by | PO delivery term | Waranty end | Q'ty | Project Value | Actual Delivery term | Max LD | LD Risk | Max LD Amount | Extra cost | Change order | Change order amount | Storage fee | Storage fee amount | PO Date | Original Delivery Date | Days late | Estimated shipdate | Actual shipdate | Balance | Project Phrase | Status | Number of Status | Progress
Project Engineer1 | 2023 | 18210304 | Customer1 | Project1 | Heater | New | USA | FOB |  | 3 | 2363614.45 | FCA | 0% | No | 0 | 0 | No | 0 | No | 0 | 2023-07-14 | 2024-06-21 | 470 | #N/A | 2025-10-04 | 979461.15 | Final Document | Shipped | 100 | 100%
Project Engineer1 | 2023 | 18210304 | Customer1 | Project1 | Control Panel | New | USA | FOB |  | 3 | 0 | FCA | 0% | No | 0 | 0 | Yes | 19003 | No | 0 | 2023-07-14 | 2024-06-21 | 453 | #N/A | 2025-09-17 | 0 | Final Document | Shipped | 100 | 100%
Project Engineer1 | 2023 | 18291861 | Customer2 | Project2 | Heater | Repeat | USA | EXW |  | 1 | 518196.05 | EXW | 0% | No | 0 | 0 | No | 0 | No | 0 | 2023-11-14 | 2024-11-12 | 378 | #N/A |  | 518196.05 | Completed | Shipped | 100 | 100%
Project Engineer1 | 2024 | 18407648 | Customer3 | Project3 | Heater | New | USA | FOB |  | 4 | 831455 | FOB | -5% | Yes | -41572.75 | 0 | No | 0 | No | 0 | 2024-04-22 | 2025-07-07 | 141 | #N/A |  | 498873 | Procurement | Delayed | 16 | 20%
Project Engineer1 | 2024 | 18492257 | Customer4 | Project4 | Heater | Repeat | Spain | EXW |  | 1 | 107400 | EXW | -5% | No | 0 | -4475.408 | Yes | 6000 | Yes | 0 | 2024-08-01 | 2025-03-13 | 257 | #N/A |  | 60860 | Shipping | Delayed | 100 | 95%
Project Engineer1 | 2024 | 18492257 | Customer4 | Project4 | Control Panel | Repeat | China | EXW |  | 1 | 0 | EXW | 0% | No | 0 | 0 | Yes | 0 | No | 0 | 2024-08-01 | 2025-03-13 |  | #N/A |  | 46540 | Completed | Shipped | 100 | 100%
Project Engineer1 | 2025 | 18664359 | Customer4 | Project4 | Heater | Repeat | Spain | EXW |  | 1 | 286400 | EXW | -5% | No | -14320 | 0 | Yes | 10500 | No | 0 | 2025-04-16 | 2025-11-07 | 18 | #N/A |  | 286400 | Final inspection | Delayed | 90 | 80%
Project Engineer1 | 2025 | 18721178 | Customer4 | Project5 | Control Panel | Repeat | China | EXW |  | 4 | 368740 | EXW | -5% | No | -18437 | 0 | No | 0 | No | 0 | 2025-04-28 | 2026-02-04 | -71 | #N/A |  | 0 | Fabrication | On track | 45 | 50%
Project Engineer2 | 2022 | 17939411 | Customer5 | Project6 | Heater | New | USA | FOB |  | 4 | 6710454.03 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2022-08-02 | 2023-11-29 | 727 | #N/A |  | 5872569.35 | Fabrication | Delayed | 38 | 40%
Project Engineer2 | 2022 | 17939411 | Customer5 | Project6 | Control Panel | New | USA | FOB |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  |  | #N/A |  | 0 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2020 | 17283462 | Customer5 | Project7 | Heater | New | USA | FOB |  | 4 | 3454700 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2020-08-05 | 2022-07-13 | 1231 | #N/A |  | 2831989.8954 | Fabrication | Delayed | 38 | 40%
Project Engineer2 | 2020 | 17283462 | Customer5 | Project7 | Control Panel | New | USA | FOB |  | 4 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  |  | #N/A |  | 0 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2023 | 18254957 | Customer6 | Project8 | Heater | New | USA | FOB |  |  | 1589287.3 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2023-09-15 | 2024-07-28 | 485 | #N/A |  | 1294261.29 | Fabrication | Delayed | 40 | 45%
Project Engineer2 | 2023 | 18254957 | Customer6 | Project8 | Control Panel | New | China | FOB |  |  | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  |  | #N/A |  | 0 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2023 | 18188317 | Customer7 | Project9 | Heater | New | USA | FOB |  | 1 | 4943980 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2023-06-16 | 2024-12-07 | 353 | #N/A |  | 4943980 | Fabrication | Delayed | 16 | 20%
Project Engineer2 | 2023 | 18188317 | Customer7 | Project9 | Control Panel | New | China | FOB |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 |  |  |  | #N/A | 2025-10-03 | 0 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Heater | New | USA |  |  | 7 | 10692464.76 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2023-08-22 | 2025-03-01 | 269 |  |  | 1000558.09 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Control Panel | New | China |  |  | 3 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0 | Final Document | Shipped | 99 | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Vessel | New | South Korea |  |  | 5 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | [5 empty] | 0 | Final Document | Shipped | 99 | 100%
Project Engineer3 | 2023 | 18185328 | Customer9 | Project11 | Heater | New | USA | EXW |  | 2 | 311639 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2023-06-09 | 2023-11-29 | 727 | #N/A |  | 17452.5 | Final Document | Shipped | 99 | 100%
Project Engineer3 | 2023 | 18351480 | Customer10 | Project12 | Heater | Repeat | USA | EWX |  | 1 | 1079706.52 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2024-02-02 | 2025-01-11 | 318 | #N/A |  | 647822.48 | Fabrication | Delayed | 35 | 35%
Project Engineer3 | 2024 | 18649372 | Customer11 | Project13 | Heater | New | Spain | EWX |  | 2 | 370530 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-03-18 | 2025-10-21 | 35 | #N/A |  | 222318 | Fabrication | On track | 40 | 45%
Project Engineer3 | 2024 | 18649372 | Customer11 | Project13 | Control Panel | New | China | EWX |  | 2 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-03-18 | 2025-10-21 | 35 | #N/A |  | 0 | Fabrication | On track | 45 | 50%
Project Engineer3 | 2025 | 18704665 | Customer12 | Project14 | Control Panel | Repeat | France | EWX |  | 2 | 154638.1 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-06-03 | 2026-01-07 | -43 | #N/A |  | 154638.1 | Prepare document | On track | 8 | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Heater | New | USA | FCA |  | 1 | 1509175.85 |  | -10% |  | -150917.585 | 0 |  | 0 |  | 0 | 2025-09-27 | 2026-09-29 | -308 | 2026-06-22 |  | 1509175.85 | Prepare document | On track | 8 | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Heater | New | USA | FCA |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-09-27 | 2026-09-29 | -308 | 2026-06-22 |  | 0 | Prepare document | On track | 8 | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Control Panel | New | USA | FCA |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-09-27 | 2026-09-29 | -308 | 2026-06-22 |  | 0 | Prepare document | On track | 8 | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Control Panel | New | USA | FCA |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-09-27 | 2026-09-29 | -308 | 2026-06-22 |  | 0 | Prepare document | On track | 8 | 10%
Project Engineer1 | 2025 | 18768883 | Customer14 | Project16 | Heater | Repeat | USA | EWX |  | 1 | 841776.14 |  | -5% |  | -42088.807 | 0 |  | 0 |  | 0 | 2025-09-05 | 2027-02-12 | -444 | 2026-11-05 |  | 841776.14 | Prepare document | On track | 8 | 10%
Project Engineer1 | 2025 | 18800831 | Customer4 | Project17 | Heater | Repeat | Spain | EWX |  | 1 | 257437.8 |  | -5% |  | -12871.89 | 0 |  | 0 |  | 0 | 2025-10-29 | 2026-06-02 | -189 | 2026-02-23 |  | 257437.8 | Prepare document | On track | 8 | 10%
Project Engineer1 | 2025 | 18800831 | Customer4 | Project17 | Control Panel | Repeat | China | EWX |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-10-29 | 2026-06-02 | -189 | 2026-02-23 |  | 0 | Prepare document | On track | 8 | 10%
Project Engineer1 | 2025 | 18798633 | Customer15 | Project18 | Heater | Repeat | USA |  |  | 1 | 605020 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-10-28 | 2026-10-08 | -317 | 2026-07-01 |  | 605020 | Prepare document | On track | 8 | 10%
Project Engineer1 | 2025 | 18798633 | Customer15 | Project18 | Control Panel | Repeat | USA |  |  | 1 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 2025-10-28 | 2026-10-08 | -317 | 2026-07-01 |  | 0 | Prepare document | On track | 8 | 10%
Formulas:
Days late = TODAY()-[Original Delivery Date]

## Invoice
Project year | SEQ | Project Engineer | Sale order No. | Customer | Total amount | Percentage of amount | Invoice value | Currency unit | Invoice plan date | Issued Date |  | Invoice due date | Plan payment date | Expected Payment date | Actual Payment received date | Plan Delayed | Actual Delayed | Claim Plan 2025 | Payment Status
Project Engineer1 | 1 | Project Engineer1 | 18291861 | Customer2 | 2026465 | 30% | 607939.5 | USD | 2025-08-21 | 2025-05-14 | 2025-08-21 | 30 | 2025-09-20 | 2025-09-20 | 2025-10-20 | -99 |  | 607939.5 | Paid
2023 | 2 | Project Engineer1 | 18291861 | Customer2 | 0 | 70% | 1418525.5 | USD | 2025-11-06 | 2025-08-08 | 2025-11-15 | 30 | 2025-12-06 | 2025-12-15 |  |  |  | 1418525.5 | Invoiced
2022 | 5 | Project Engineer1 | 17999583 | Customer14 | 2933000 | 5% | 20950 | USD | 2024-02-06 | 2023-08-27 | 2023-12-04 | 45 | 2024-03-22 | 2024-01-18 | 2025-10-07 | -163 | 628 | 146650 | Paid
2023 | 3 | x | 18210304 | Customer1 | 9376206 | 20% | 264091 | USD | 2024-12-13 | 2024-12-13 | 2025-03-22 | 60 | 2025-02-11 | 2025-05-21 | 2025-07-15 | 0 | 55 | 1848637 | Paid
2023 | 4 | Project Engineer1 | 18210304 | Customer1 | 0 | 30% | 415140 | USD | 2025-09-06 | 2025-05-14 | 2025-08-21 | 60 | 2025-11-05 | 2025-10-20 | 2025-12-05 | -115 |  | 2905980 | Paid
2023 | 5 | Project Engineer1 | 18210304 | Customer1 | 0 | 10% | 132045.5 | USD | 2025-12-07 | 2025-08-08 | 2025-11-15 | 60 | 2026-02-05 | 2026-01-14 |  |  |  | 924318.5 | Invoiced
2024 | 2 | Project Engineer1 | 18407648 | Customer3 | 3251500 | 30% | 139350 | USD | 2025-07-07 | 2024-03-27 | 2024-07-04 | 30 | 2025-08-06 | 2024-08-03 | 2025-09-04 | -467 | 397 | 975450 | Paid
2024 | 3 | Project Engineer1 | 18407648 | Customer3 | 0 | 50% | 232250 | USD | 2025-11-06 |  |  | 30 | 2025-12-06 |  |  |  | 0 | 1625750 | Not invoiced
Project Engineer2 | 4 | Project Engineer1 | 18407648 | Customer3 | 0 | 10% | 46450 | USD | 2025-12-07 |  |  | 30 | 2026-01-06 |  |  |  | 0 | 325150 | Not invoiced
2024 | 1 | Project Engineer1 | 18492257 | Customer4 | 462000 | 50% | 30000 | USD | 2025-08-22 | 2025-05-14 | 2025-08-21 | 30 | 2025-09-21 | 2025-09-20 |  | -100 |  | 210000 | Aging
2024 | 2 | Project Engineer1 | 18492257 | Customer4 | 0 | 50% | 36000 | USD | 2025-11-06 | 2025-07-24 | 2025-10-31 | 30 | 2025-12-06 | 2025-11-30 |  |  |  | 252000 | Invoiced
2025 | 1 | Project Engineer1 | 18664359 | Customer4 | 1193500 | 15% | 24000 | USD | 2025-08-07 | 2025-05-15 | 2025-08-22 | 30 | 2025-09-06 | 2025-09-21 | 2025-12-03 | -84 | 73 | 168000 | Paid
2025 | 2 | Project Engineer1 | 18664359 | Customer4 | 0 | 35% | 61250 | USD | 2025-11-06 | 2025-07-24 | 2025-10-31 | 30 | 2025-12-06 | 2025-11-30 |  |  |  | 428750 | Aging
2025 | 3 | Project Engineer1 | 18664359 | Customer4 | 0 | 50% | 596750 | USD | 2025-11-14 |  |  | 30 | 2025-12-14 |  |  |  | 0 | 596750 | Not invoiced
2025 | 1 | Project Engineer1 | 18721178 | Customer4 | 1442000 | 15% | 216300 | USD | 2025-08-20 | 2025-05-14 | 2025-08-21 | 30 | 2025-09-19 | 2025-09-20 |  | -98 |  | 216300 | Invoiced
2025 | 2 | Project Engineer1 | 18721178 | Customer4 | 0 | 35% | 504700 | USD | 2025-11-18 |  |  | 30 | 2025-12-18 |  |  |  | 0 | 504700 | Not invoiced
2025 | 3 | Project Engineer1 | 18721178 | Customer4 | 0 | 50% | 721000 | USD | 2026-02-04 |  |  | 30 | 2026-03-06 |  |  |  | 0 | 721000 | Not invoiced
2022 | 1 | Project Engineer3 | 18110680/18110687 | Customer15 | 1015000 | 100% | 145000 | USD | 2025-04-08 | 2025-02-20 | 2025-05-30 | 30 | 2025-05-08 | 2025-06-29 | 2025-08-30 | -47 | 62 | 1015000 | Paid
2022 | 1 | Project Engineer3 | 18112129 | Customer4 | 444500 | 100% | 63500 | USD | 2025-03-09 | 2024-12-11 | 2025-03-20 | 30 | 2025-04-08 | 2025-04-19 | 2025-06-19 | -88 | 61 | 444500 | Paid
Project Engineer3 | 4 | Project Engineer3 | 18185328 | Customer16 | 1211000 | 35% | 60550 | USD | 2025-03-24 | 2025-03-11 | 2025-06-18 | 30 | 2025-04-23 | 2025-07-18 | 2025-06-28 | -13 | -20 | 423850 | Paid
2023 | 5 | Project Engineer3 | 18185328 | Customer16 | 0 | 5% | 9750 | USD | 2024-08-07 |  |  | 30 | 2024-09-06 |  |  |  | 0 | 68250 | Not invoiced
2023 | 2 | Project Engineer3 | 18351480 | Customer17 | 4222316 | 20% | 120637.6 | USD | 2025-06-28 | 2025-04-02 | 2025-07-10 | 30 | 2025-07-28 | 2025-08-09 |  | -87 |  | 844463.2 | Aging
2023 | 3 | Project Engineer3 | 18351480 | Customer17 | 0 | 50% | 301594 | USD | 2025-11-05 |  |  | 30 | 2025-12-05 |  |  |  | 0 | 2111158 | Not invoiced
2023 | 4 | Project Engineer3 | 18351480 | Customer17 | 0 | 10% | 60318.8 | USD | 2025-11-22 |  |  | 30 | 2025-12-22 |  |  |  | 0 | 422231.6 | Not invoiced
2022 | 1 | Project Engineer3 | 18105486 | Customer18 | 4838957.97 | 45% | 311075.87 | USD | 2024-12-24 | 2024-10-09 | 2025-01-16 | 30 | 2025-01-23 | 2025-02-15 | 2025-04-18 | -76 | 62 | 2177531.09 | Paid
2022 | 2 | Project Engineer3 | 18105486 | Customer18 | 0 | 18% | 124430.35 | USD | 2024-12-24 | 2024-10-15 | 2025-01-22 | 30 | 2025-01-23 | 2025-02-21 | 2025-04-18 | -70 | 56 | 871012.45 | Paid
2022 | 3 | Project Engineer3 | 18105486 | Customer18 | 0 | 27% | 186645.52 | USD | 2025-03-09 | 2025-02-25 | 2025-06-04 | 30 | 2025-04-08 | 2025-07-04 | 2025-09-05 | -12 | 63 | 1306518.64 | Paid
2022 | 4 | Project Engineer3 | 18105486 | Customer18 | 0 | 10% | 69127.97 | USD | 2025-10-07 |  |  | 30 | 2025-11-06 |  |  |  | 0 | 483895.79 | Not invoiced
2024 | 1 | Project Engineer3 | 18649372 | Customer11 | 1449000 | 20% | 41400 | USD | 2025-04-15 | 2025-03-06 | 2025-06-13 | 30 | 2025-05-15 | 2025-07-13 | 2025-07-29 | -40 | 16 | 289800 | Paid
2024 | 2 | Project Engineer3 | 18649372 | Customer11 | 0 | 20% | 41400 | USD | 2025-08-02 | 2025-05-13 | 2025-08-20 | 30 | 2025-09-01 | 2025-09-19 |  | -81 |  | 289800 | Aging
2024 | 3 | Project Engineer3 | 18649372 | Customer11 | 0 | 20% | 41400 | USD | 2025-09-09 | 2025-06-16 | 2025-09-23 | 30 | 2025-10-09 | 2025-10-23 |  | -85 |  | 289800 | Aging
2024 | 4 | Project Engineer3 | 18649372 | Customer11 | 0 | 35% | 72450 | USD | 2025-10-21 |  |  | 30 | 2025-11-20 |  |  |  | 0 | 507150 | Not invoiced
2024 | 5 | Project Engineer3 | 18649372 | Customer11 | 0 | 5% | 10350 | USD | 2025-12-07 |  |  | 30 | 2026-01-06 |  |  |  | 0 | 72450 | Not invoiced
2019 | 5 | Project Engineer2 | 16942702 | Customer19 | 17115700 | 10% | 244510 | USD | 2025-03-24 |  |  | 45 | 2025-05-08 |  |  |  | 0 | 1711570 | Not invoiced
2020 | 4 | Project Engineer2 | 17175578 | Customer20 | 9857022 | 10% | 175301.6 | USD | 2024-02-06 | 2024-10-09 | 2025-01-16 | 45 | 2024-03-22 | 2025-03-02 |  | 246 |  | 1227111.2 | Aging
2021 | 7 | Project Engineer2 | 17662855 | Customer21 | 620053 | 10% | 15257.9 | USD | 2024-05-02 | 2024-01-24 | 2024-05-02 | 30 | 2024-06-01 | 2024-06-01 | 2025-07-03 | -99 | 397 | 106805.3 | Paid
2021 | 3.2 | Project Engineer2 | 17805319 | Customer22 | 11306359.68 | 20% | 323038.85 | USD | 2025-03-09 | 2024-11-29 | 2025-03-08 | 45 | 2025-04-23 | 2025-04-22 | 2025-06-06 | -100 | 45 | 2261271.95 | Paid
2021 | 4 | Project Engineer2 | 17805319 | Customer22 | 0 | 10% | 161519.42 | USD | 2025-08-07 |  |  | 45 | 2025-09-21 |  |  |  | 0 | 1130635.94 | Not invoiced
2022 | 2 | Project Engineer2 | 17939411 | Customer23 | 26241999 | 10% | 424498.3 | USD | 2024-12-24 | 2024-10-28 | 2025-02-04 | 45 | 2025-02-07 | 2025-03-21 | 2025-08-16 | -57 | 148 | 2971488.1 | Paid
2022 | 3 | Project Engineer2 | 17939411 | Customer23 | 0 | 25% | 942214.25 | USD | 2025-08-07 | 2025-06-16 | 2025-09-23 | 45 | 2025-09-21 | 2025-11-07 |  | -52 |  | 6595499.75 | Aging
2022 | 4 | Project Engineer2 | 17939411 | Customer23 | 0 | 55% | 2068746.35 | USD | 2026-02-21 |  |  | 45 | 2026-04-07 |  |  |  | 0 | 14481224.45 | Not invoiced
2022 | 5 | Project Engineer2 | 17939411 | Customer23 | 0 | 5% | 188067.85 | USD | 2026-04-08 |  |  | 45 | 2026-05-23 |  |  |  | 0 | 1316474.95 | Not invoiced
2023 | 2 | Project Engineer2 | 18188317 | Customer24 | 19334000 | 15% | 414300 | USD | 2024-08-07 | 2025-04-30 | 2025-08-07 | 30 | 2024-09-06 | 2025-09-06 | 2025-08-30 | 266 | -7 | 2900100 | Paid
2023 | 3 | Project Engineer2 | 18188317 | Customer24 | 0 | 20% | 552400 | USD | 2025-09-22 |  |  | 30 | 2025-10-22 |  |  |  | 0 | 3866800 | Aging
2023 | 4 | Project Engineer2 | 18188317 | Customer24 | 0 | 50% | 1381000 | USD | 2025-12-19 |  |  | 30 | 2026-01-18 |  |  |  | 0 | 9667000 | Not invoiced
2023 | 5 | Project Engineer2 | 18188317 | Customer24 | 0 | 5% | 138100 | USD | 2026-02-01 |  |  | 30 | 2026-03-03 |  |  |  | 0 | 966700 | Not invoiced
2023 | 4 | Project Engineer2 | 18239263 | Customer25 | 41814108 | 5% | 298672.2 | USD | 2025-08-07 | 2025-06-16 | 2025-09-23 | 45 | 2025-09-21 | 2025-11-07 |  | -52 |  | 2090705.4 | Aging
2023 | 5.3 | Project Engineer2 | 18239263 | Customer25 | 0 | 2.8% | 166667 | USD | 2025-07-13 | 2025-04-02 | 2025-07-10 | 45 | 2025-08-27 | 2025-08-24 | 2025-08-23 |  | -1 | 1166669 | Paid
2023 | 5.4 | Project Engineer2 | 18239263 | Customer25 | 0 | 4.8% | 284405.7 | USD | 2025-04-14 | 2025-01-23 | 2025-05-02 | 45 | 2025-05-29 | 2025-06-16 | 2025-06-19 | -81 | 3 | 1990839.9 | Paid
2023 | 5.5 | Project Engineer2 | 18239263 | Customer25 | 0 | 4.8% | 284405.7 | USD | 2025-04-14 | 2025-01-23 | 2025-05-02 | 45 | 2025-05-29 | 2025-06-16 | 2025-06-19 | -81 | 3 | 1990839.9 | Paid
2023 | 5.6 | Project Engineer2 | 18239263 | Customer25 | 0 | 4.8% | 284405.7 | USD | 2025-04-14 | 2025-01-23 | 2025-05-02 | 45 | 2025-05-29 | 2025-06-16 | 2025-06-19 | -81 | 3 | 1990839.9 | Paid
2023 | 5.7 | Project Engineer2 | 18239263 | Customer25 | 0 | 4.8% | 284405.7 | USD | 2025-04-14 | 2025-01-23 | 2025-05-02 | 45 | 2025-05-29 | 2025-06-16 | 2025-06-19 | -81 | 3 | 1990839.9 | Paid
2023 | 5.8 | Project Engineer2 | 18239263 | Customer25 | 0 | 5.3% | 318391.3 | USD | 2025-08-31 | 2025-05-27 | 2025-09-03 | 45 | 2025-10-15 | 2025-10-18 |  | -96 |  | 2228739.1 | Aging
2023 | 6 | Project Engineer2 | 18239263 | Customer25 | 0 | 10% | 597344.4 | USD | 2025-10-02 |  |  | 45 | 2025-11-16 |  |  |  | 0 | 4181410.8 | Not invoiced
2023 | 1 | Project Engineer2 | 18254957 | Customer22 | 6374690 | 10% | 91067 | USD | 2024-12-23 | 2025-01-07 | 2025-04-16 | 45 | 2025-02-06 | 2025-05-31 | 2025-05-01 | 15 | -30 | 637469 | Paid
2023 | 2 | Project Engineer2 | 18254957 | Customer22 | 0 | 20% | 182134 | USD | 2024-12-29 | 2025-01-17 | 2025-04-26 | 45 | 2025-02-12 | 2025-06-10 | 2025-06-04 | 19 | -6 | 1274938 | Paid
2023 | 3 | Project Engineer2 | 18254957 | Customer22 | 0 | 60% | 546402 | USD | 2025-09-27 |  |  | 45 | 2025-11-11 |  |  |  | 0 | 3824814 | Not invoiced
2023 | 4 | Project Engineer2 | 18254957 | Customer22 | 0 | 10% | 91067 | USD | 2025-10-19 |  |  | 45 | 2025-12-03 |  |  |  | 0 | 637469 | Not invoiced
2025 | 1 | Project Engineer1 | 18768883 | Customer14 | 3291862 | 15% | 493779.3 | USD | 2025-11-07 | 2025-07-25 | 2025-11-01 | 30 | 2025-12-07 | 2025-12-01 |  |  |  | 493779.3 | Aging
2025 | 2 | Project Engineer1 | 18768883 | Customer14 | 0 | 35% | 1152151.7 | USD | 2026-06-10 | [7 empty] | 0 | 1152151.7 | Not invoiced
2025 | 3 | Project Engineer1 | 18768883 | Customer14 | 0 | 50% | 1645931 | USD | 2027-02-12 | [7 empty] | 0 | 0 | Not invoiced
2025 | 1 | Project Engineer3 | 18793810 | Customer13 | 5901805 | 10% | 590180.5 | USD | [8 empty] | 0 | 590180.5 | Not invoiced
2025 | 2 | Project Engineer3 | 18793810 | Customer13 | 0 | 20% | 1180361 | USD | [8 empty] | 0 | 0 | Not invoiced
2025 | 3 | Project Engineer3 | 18793810 | Customer13 | 0 | 10% | 590180.5 | USD | [8 empty] | 0 | 0 | Not invoiced
2025 | 4 | Project Engineer3 | 18793810 | Customer13 | 0 | 50% | 2950902.5 | USD | [8 empty] | 0 | 0 | Not invoiced
2025 | 5 | Project Engineer3 | 18793810 | Customer13 | 0 | 10% | 590180.5 | USD | 2026-06-22 | [7 empty] | 0 | 0 | Not invoiced
2025 | 1 | Project Engineer1 | 18800831 | Customer4 | 1006740 | 15% | 151011 | USD | 2025-10-22 | [7 empty] | 0 | 151011 | Not invoiced
2025 | 2 | Project Engineer1 | 18800831 | Customer4 | 0 | 35% | 352359 | USD | 2026-02-15 | [7 empty] | 0 | 0 | Not invoiced
2025 | 3 | Project Engineer1 | 18800831 | Customer4 | 0 | 50% | 503370 | USD | 2026-02-23 | [7 empty] | 0 | 0 | Not invoiced
Formulas:
Plan payment date = [Invoice plan date]+[Invoice due date]